## PRODUCTS
Business Problem | Is it a physical product, service or something abstract? | Does this look to be a Empirical or Defined problem? | Who are the possible end-users for this product? | Who are the possible stakeholders (other than the end users) for this product? | From end-user perspective | From stakeholder perspective
Aggregator platform for wildlife resort and safari bookings | Service | Empirical | Tourists, Wildlife Enthusiasts, Travel Bloggers | Resort Owners, Forest Departments, Investors | Convenience, Customer Satisfaction, Improved Booking Experience | Revenue growth, Market penetration, Brand awareness
Digital pest control scheduling system | Service | Defined | Homeowners, Facility Managers | Pest control companies, Health departments | Hygiene, Safety, Time Saving | Operational efficiency, Better scheduling
R&D for developing a vaccine for a new disease (Covid-19) | Abstract | Empirical | Pharmaceutical Companies | WHO, Research Institutes, Government, Shareholders | Brand Value, Improved product and services, New products, Improved Quality, Innovation/patents, Competitive Advantage, Customer Satisfaction | Improvement in Global Health, Recognition
Platform for motivational content from spiritual leaders | Abstract | Defined | Spiritual Seekers, Youth, General Public | Religious Organizations, Sponsors, Event Hosts | Inspiration, Emotional Wellbeing, Mental Clarity | Public engagement, Social influence
CRM system for a bank sales team to sell new products to existing customers | Service | Defined | Bank Sales Executives, Relationship Managers | Bank Management, IT Teams, Product Managers, CRM Vendors | Increased Efficiency, Customer Retention, Personalization | Ease of managing leads, faster customer service, Higher conversion rates, better product targeting, employee productivity
Setup of a call center to address issues of customers | Service | Defined | Bank Customers, General Public | Customer Support Teams, Operations Managers, BPO Providers, Quality Analysts | Better Customer Experience, Faster Issue Resolution, Customer Loyalty | Quick resolution, 24/7 support, trust, Improved service reputation, operational monitoring, feedback collection
Setup of a call center to address issues of customers | Service | Defined | Bank Customers, General Public | Customer Support Teams, Operations Managers, BPO Providers, Quality Analysts | Better Customer Experience, Faster Issue Resolution, Customer Loyalty | Quick resolution, 24/7 support, trust

## PO
Sr. | Statements about Product Owner | True/False
1 | Product Owner may delegate the responsibility of writing requirements to someone else | TRUE
2 | The Product Owner may represent the needs of many stakeholders in the Product Backlog | TRUE
3 | If a stakeholder wants to change the Product Backlog then he/she can do so by convincing the Scrum Master | FALSE
4 | Developers cannot directly talk to the stakeholders. They must talk to the PO first | FALSE
5 | For Product Owners to succeed, the entire organization must respect their decisions | TRUE
6 | A Product Owner must ensure that the Product Backlog is transparent, visible and understood by every Developer | FALSE
7 | The Product Owner is accountable for maximizing the value of the product resulting from the work of the Scrum Team. How this is done may vary widely across organizations, Scrum Teams, and individuals. | TRUE
8 | The Scrum Master serves the PO by helping him/her find techniques for effective Product Goal definition and Product Backlog management | TRUE
9 | The Product Goal is the long-term objective for the Scrum Team. They must fulfill (or abandon) one objective before taking on the next. | TRUE
10 | Product Owner should be aware about various Business Analysis techniques to make the product development effective | TRUE

## VISION
Field | Details
Product Name | Wild Stays
Tagline | Transforming the way people experience jungle stays.
What is the product? | Aggregator Mobile App for Wild Life Resorts bookings, safari experiences, and eco-tourism.
Vision Statement | To become India’s go-to wildlife experience and resort booking platform by connecting eco-conscious travelers with verified forest stays.
Mission Statement | Enhancing access to nature while promoting sustainable tourism through an intuitive, eco-friendly platform.
Name Suggestions | Wild Traits, Jungle Heaven, Jungle Book, Wild Escape

## PRODUCT GOAL
Vision Statement (Summary) :
Why? | Reasons | Why should users use this product? What does the product solve? | People struggle to find verified wildlife stays. Wild Stays centralizes bookings, ensures trust and improves access to unique jungle experiences.
Who? | Target Customers | Who is the target customer? | Nature lovers, wildlife photographers, eco-conscious families, millennials seeking adventure and foreign tourists.
What? | Key Differentiating Features | What makes the product unique? What are the key features? | India’s first dedicated aggregator for wildlife resorts and safaris. Verified listings, real reviews, sustainability ratings and real-time bookings.
When? | Timescales | When is the product MVP expected to be delivered? | 6 months (MVP), followed by iterative bi-weekly sprint releases.

## Customers and Users
Basis---> | Age | Purpose of Travel | Location | Budget | Type of Services
| Students | Wild Life Enthusiast | North | Economy | Resort
| Young Adults | Nature Lovers | South | Premium | Safari
| Older Adults | Special Occasion | East | Mid | Adventure
| Sr Citizens | Pilgrimage + Nature | West | Mid | Eco-Stays
| Families | Vacation with Children | Central | Premium | Resort + Safari
| Foreign Tourists | Exotic Wildlife Tours | All Zones | Premium | Guided Safaris
Exercise 1 | Sample user segments
s1 - Students, nature lovers, north, Economy, Adventure
s2 - Older Adults, Special Occasion, South, Premium, Resort
s3
Exercise 2 | Reason for Chasm | Government Directives: Ban for direct Wildlife resort booking
| Choice of segment which will help cross the Chasm | S2
| Reason for the choice of the segment | Provide more luxurious resort experience & destination wedding / occasion
Exercise 3 |  | S |  | M |  | T
| Strategic Goal 1 | Retain S2 from going outside India for Wedding / Occasion By Offering premium features to Loyal and repeated visitors |  | Retain 10k customer bookings |  | One Quarter
| Strategic Goal 2 | Target S1 by marketing adding influencers |  | Increase 5k |  | One quarter
| Strategic Goal 3 | Tie up with tourism boards and travel agencies |  | increase users by 40% |  | One Quarter

## Epics
Sr | Epic | Name
1 | User Registration | Madhu
2 | Booking Engine-Login | Mayur
3 | Payment Gateway-Security | Mayukha
4 | Payment | Malavika
5 | Home Page | Meenakshi
6 | Application Design | Manisha
7 | Booking Form | Varun
8 | Aggregation | Mohit
9 | Audit | Mani
10 | Catalogue | Venkat

## PB
Attributes | Epic | Item Type | Labels | Item Description | Priority | Order | Estimate | Release#
PB Item | Application Design | Functionality (user story) | User Interface | Design clean and intuitive screens for end-users | M | 1 | 8
PB Item | Application Design | Functionality (user story) | Search Functionality | Enable users to search content using keywords or filters | S | 26 | 8
PB Item | Application Design | Functionality (user story) | User Registration/Login | Allow users to sign up, log in, and manage accounts | M | 2 | 8
PB Item | Application Design | Functionality (user story) | Error Handling | Display clear and helpful error messages | M | 3 | 13
PB Item | Login | Functionality (user story) | Login GUI | Create login screen with required fields | M | 4 | 5
PB Item | Login | Functionality (user story) | Show/reset capta | Add a capta image or text and reset function | S | 25 | 5
PB Item | Login | Tech (Task) | Call API to login | Upon tap on Login call the API | M | 5 | 8
PB Item | Login | Functionality (user story) | Error handling | Show error message on screen in case credentials don't match | S | 27 | 13
PB Item | Security | Tech (Task) | Role based Access Control | define access by roles such as admin , vendor , user | M | 20 | 13
PB Item | Security | Tech (Task) | Data Encryption | SLS/TLS encryption for stored data | M | 21 | 21
PB Item | Security | Tech (Task) | Session Management | auto logout for idle sessions | S | 28 | 5
PB Item | Security | Tech (Task) | Data Backup and Recovery | Backup data regularly | S | 29 | 21
PB Item | Security | Tech (Task) | GDPR Compliance | Follow national and international protection laws | M | 22 | 13
PB Item | Payment | Functionality (user story) | payment method and integration with payment gateway | adding and verifying the type of payment method and integrating the payment type | M | 14 | 21
PB Item | Payment | Functionality (user story) | paymnet notification | userface for payment notifcation | S | 30 | 5
PB Item | Payment | Functionality (user story) | exception handling | notification in case the payment fails | M | 15 | 13
PB Item | Payment | Functionality (user story) | Payment UI | look and feel of payment interface | M | 16 | 5
PB Item | Home Page | Functionality (user story) | Booking button | to encourage users to intitiate the booking process | M | 6 | 5
PB Item | Home Page | Functionality (user story) | Navigation Menu | to move between the different sections and features of the app | M | 7 | 5
PB Item | Home Page | Functionality (user story) | Site Search | quickly find specific content or products within the app | M | 8 | 5
PB Item | Home Page | Tech (Task) | Mobile responsiveness | homepage should be optimised for different screen sizes | S | 31 | 13
PB Item | Audit | Functionality (user story) | History Tracking | Tracking the booking, user & payment details in DB | M | 17 | 8
PB Item | Audit | Functionality (user story) | Time Stamp | Tracking the time details of each booking in DB | M | 18 | 5
PB Item | Audit | Functionality (user story) | Tracking Report | Report to show the History details | M | 19 | 8
PB Item | Audit | Tech (Task) | ETL | Pushing the data to Reporting Dashboard through ETL | S | 32 | 13
PB Item | Booking Form | Functionality (user story) | Capture input data | Provide fields to capture booking information | M | 9 | 13
PB Item | Booking Form | Functionality (user story) | Determine cost | Determine booking cost based on the number of people, resort and number of days | S | 33 | 5
PB Item | Booking Form | Tech (Task) | List resorts | Integrate with external systems to list resorts | M | 10 | 21
PB Item | Catalogue | Functionality (user story) | Resort Search | Search function with advanced filtering for resorts, adventures, safari events | S | 34 | 5
PB Item | Catalogue | Functionality (user story) | Resort List (Grid & List Views) | List of resorts and events with thumbnails and short description | M | 23 | 8
PB Item | Catalogue | Functionality (user story) | Resort Detail | Detailed information along with photos of selected Resort or Event | S | 35 | 5
PB Item | Catalogue | Tech (Task) | develop wireframes | design the wireframes for user feedback | M | 24 | 13
PB Item | Registration | None | email id /password, , | provide text fields to register with email and password | M | 11 | 8
PB Item | Registration | Tech (Task) | link from fb/google, | provide link to register by importing credentials from fb/google accounts | S | 36 | 5
PB Item | Registration | Tech (Task) | verify email | API to validate registration success through verifying email | M | 12 | 8
PB Item | Registration | Tech (Task) | accept terms and conditions, | publish terms and conditions page for agreement for registration | M | 13 | 5

## Release Planning
Problem :
How to calculate this problem Assumptions :
Sprint duration is 2 weeks and average sprint velocity is 30 points.
Team size is 10 people and cost per person per sprint is $1500 (i.e. $15000 per sprint)
How many sprints would be required to complete 100% of the “Must” and some “Should” scope in the next release?
What is the Budget for the next release?
Step 1: Understand the assumptions
Sprint duration: 2 weeks
Team velocity: 30 story points per sprint
Team size: 10 people
Cost per person per sprint: $1500
Total cost per sprint: 10 × $1500 = $15,000
Step 2: Story Points by Priority
From the PB table earlier:
Priority | Items | Total Story Points
Must (M) | 2 items | 8 (login) + 13 (payment) = 21
Should (S) | 3 items | 8 (search) + 5 (calendar) + 3 (alerts) = 16
Could (C) | 3 items | 5 (safari) + 3 (reviews) + 8 (admin) = 16
We are to deliver:
100% of Must = 21 points
Some Should = we can choose 2 out of 3 = 8 (search) + 5 (calendar) = 13 points
(This totals to 21 + 13 = 34 story points)
Step 3: Calculate No. of Sprints
Total story points for next release = 34
Velocity per sprint = 30
Sprints Required=⌈34/30⌉=⌈1.13⌉=2 Sprints​
Step 4: Calculate Budget
Each sprint cost = $15,000
2 sprints = 2 × $15,000 = $30,000
Final Answers
🔢 Number of Sprints = 2
💰 Budget for Next Release = $30,000

## User Story
As a | College Student | Given | I am on the login screen | Given | Given
I want to | access the Wild Life App | When | i enter my credentials & click login | When | When
So that | I would be able to book the resort | Then | i should be redirected to Booking Page to continue booking the resorts | Then | Then
As a | College student | Given | I am on the Payment page | Given | Given
I want to | make the payment for booking | When | i enter the payment details | When | When
So that | the booking can be confirmed & invoice can be generated | Then | the payment should be completed | Then | Then
As a | new user | Given | i am on registration page | Given | Given
I want to | register an account | When | i fill in valid information and click signup | When | When
So that | access personalized features | Then | i should see WELCOME message | Then | Then

## US
Login Scenario
As a | I want to | So that | Given | When | Then
College Student | access the Wild Life App | I would be able to book the resort | I am on the login screen | I enter my credentials & click login | I should be redirected to Booking Page to continue booking resorts
Admin | access the Wild Life App dashboard | I can manage user activities | I am on the admin login page | I enter valid admin credentials | I should be redirected to Admin Dashboard
Payment Scenario
As a | I want to | So that | Given | When | Then
College Student | access the Wild Life App | I would be able to book the resort | I am on the login screen | I enter my credentials & click login | I should be redirected to Booking Page to continue booking resorts
Admin | access the Wild Life App dashboard | I can manage user activities | I am on the admin login page | I enter valid admin credentials | I should be redirected to Admin Dashboard
Registration Scenario
As a | I want to | So that | Given | When | Then
New User | register an account | access personalized features | I am on registration page | I fill in valid information and click signup | I should see WELCOME message
Support Agent | register test accounts | verify registration workflows | I am on the test registration page | I enter dummy data | The system should allow test account and show confirmation